## Sheet1
Schedule of Activities - RFP #21-RFP-IT-460
Task | Jul 16 |  |  | Jul 19 | Jul 20 | Jul 21 | Jul 22 | Jul 23 |  |  | Jul 26 | Jul 27 | Jul 28 | Jul 29 | Jul 30 |  |  | Aug 02 | Aug 03 | Aug 04 | Aug 05 | Aug 06 |  |  | Aug 09 | Aug 10 | Aug 11 | Aug 12 | Aug 13 |  |  | Aug 16 | Aug 17
RFP Released | X | S | S | [5 empty] | S | S | [5 empty] | S | S | [5 empty] | S | S | [5 empty] | S | S
RFP Discovery - Established Interest |  | S | S |  | X | X |  |  | S | S | [5 empty] | S | S | [5 empty] | S | S | [5 empty] | S | S
Initial Analysis |  | S | S |  |  |  | X | X | S | S | [5 empty] | S | S | [5 empty] | S | S | [5 empty] | S | S
Go/No-Go Assessment & Kickoff Call |  | S | S | [5 empty] | S | S | X | X |  |  |  | S | S | [5 empty] | S | S | [5 empty] | S | S
Compliance Matrix & Timeline Creation |  | S | S | [5 empty] | S | S |  | X | X |  |  | S | S | [5 empty] | S | S | [5 empty] | S | S
Gather Documents & Content Library Review |  | S | S | [5 empty] | S | S |  | X | X | X | X | S | S | X |  |  |  |  | S | S | [5 empty] | S | S
Competitor Analysis & Clarifications Call or Email |  | S | S | [5 empty] | S | S |  |  |  | X | X | S | S | [5 empty] | S | S | [5 empty] | S | S
Last Day for Proposer Questions |  | S | S | [5 empty] | S | S |  |  |  |  | X | S | S | [5 empty] | S | S | [5 empty] | S | S
Drafting: Technical and Narrative Sections |  | S | S | [5 empty] | S | S | [5 empty] | S | S | X | X | X | X |  | S | S | [5 empty] | S | S
Gathering Attachments |  | S | S | [5 empty] | S | S | [5 empty] | S | S | X | X | X |  |  | S | S | [5 empty] | S | S
Internal Review & Interim Feedback |  | S | S | [5 empty] | S | S | [5 empty] | S | S |  |  | X | X |  | S | S | [5 empty] | S | S
Review Meeting |  | S | S | [5 empty] | S | S | [5 empty] | S | S |  |  |  |  | X | S | S | X |  |  |  |  | S | S
Final Draft Revisions |  | S | S | [5 empty] | S | S | [5 empty] | S | S | [5 empty] | S | S | X | X |  |  |  | S | S
Compliance Check & Final Formatting |  | S | S | [5 empty] | S | S | [5 empty] | S | S | [5 empty] | S | S |  |  | X | X |  | S | S
Verification of Submission Checklist |  | S | S | [5 empty] | S | S | [5 empty] | S | S | [5 empty] | S | S |  |  | X | X |  | S | S
Final Review: Client Review & Approval |  | S | S | [5 empty] | S | S | [5 empty] | S | S | [5 empty] | S | S |  |  |  |  | X | S | S
Submission |  | S | S | [5 empty] | S | S | [5 empty] | S | S | [5 empty] | S | S |  |  |  |  | X | S | S
RFP Deadline for Submission |  | S | S | [5 empty] | S | S | [5 empty] | S | S | [5 empty] | S | S | [5 empty] | S | S |  | X
All dates will be added to Teams Planner too. 3-2-1!
RFP Related Activity
NovalSel
Client & NovaSel